## Sheet1
| 2024-09-30 | 2024-10-14 | 2024-10-28 | 2024-11-11 | 2024-11-25 | 2024-12-09 | 2024-12-23 | 2025-01-06 | 2025-01-20 | 2025-02-03 | 2025-02-17 | 2025-03-03 | 2025-03-17 | 2025-03-31 | 2025-04-14 | 2025-04-28
Software Development | 2024-09-30: Familiarization with technologies
Initial development of demonstration application
Exploration and prototyping phase
Development of final suite of chosen algorithms
Integration of algorithms with demonstration application
Demonstration appplication completion, testing, bug fixes, and polish.
Report and Presentation | 2024-10-28: Draft report introduction
Design report layout and choose areas cover
Draft main content
Draft conclusion
Final write up
Preparation for presentation
Research | 2024-09-30: Literature review
Collect performance data of algorithms
Inclusion and analysis of data sources in report
Collect demonstration images for report
Inclusion of images in report